## Risk Management
Risk/Issue | Action | PIC
Team isn't centralized -> Impact on the management | Hold up daily meeting via Skype to manage tasks daily | PM
Schedule is really tight -> Impact on the output | Cut down the scope with the phylosophy: Do one thing and do it well (ensure to complete one scope following the initial process defined by teacher) | All team members

## 16-Nov-2015
Team members | Work Done | Plan for Tomorrow | ETA | Risk/Issue
Bach | Create WBS Assign Tasks at High Level | Track tasks daily and create daily report | Daily
Trung | Import RAW DATA to SQL Server | Import RAW DATA to SQL Server | 16/Nov - 19/Nov
Truong | Research how to create decision tree (R or Python?) | Research how to create decision tree (R or Python?) | 16/Nov - 19/Nov
Luu | Create GitHub link to centralize the project's work | Create GitHub link to centralize the project's work | 16/Nov - 17/Nov
Duc | Study Fact + Dimension database, Cube's aspect | Study Fact + Dimension database, Cube's aspect | 16/Nov - 19/Nov
Tuan | Research how to create decision tree (R or Python?) | Research how to create decision tree (R or Python?) | 16/Nov - 19/Nov

## 17-Nov-2015
Team members | Work Done | Next plan | ETA | Risk/Issue
Bach | Track tasks daily and create daily report | Track tasks daily and create daily report | Daily
Trung | Import RAW DATA to SQL Server | Import RAW DATA to SQL Server | 16/Nov - 19/Nov
Truong | Research how to create decision tree (R or Python?) | Research how to create decision tree (R or Python?) | 16/Nov - 19/Nov
Luu | Create GitHub link to centralize the project's work | Study how to create Cube | 17/Nov - 20/Nov
Duc | Study Fact + Dimension database, Cube's aspect | Study Fact + Dimension database, Cube's aspect | 16/Nov - 19/Nov
Tuan | Research how to create decision tree (R or Python?) | Research how to create decision tree (R or Python?) | 16/Nov - 19/Nov

## 18-Nov-2015
Team members | Work Done | Next plan | ETA | Risk/Issue
Bach | Track tasks daily and create daily report | Track tasks daily and create daily report | Daily
Trung | Import RAW DATA to SQL Server | Import RAW DATA to SQL Server | 16/Nov - 19/Nov
Truong | Research how to create decision tree (R or Python?) | Research how to create decision tree (R or Python?) | 16/Nov - 19/Nov
Luu | Study how to create Cube | Study how to create Cube | 17/Nov - 20/Nov
Duc | Study Fact + Dimension database, Cube's aspect | Study Fact + Dimension database, Cube's aspect | 16/Nov - 19/Nov
Tuan | Research how to create decision tree (R or Python?) | Research how to create decision tree (R or Python?) | 16/Nov - 19/Nov

## 19-Nov-2015
Team members | Work Done | Next plan | ETA | Risk/Issue
Bach | Track tasks daily and create daily report | Track tasks daily and create daily report | 20/Nov - 20/Nov
Trung | Import RAW DATA to SQL Server | Milestone meeting 1. Summarize work done this week and discuss the next step 2. Knowledge sharing 3. Troubleshoot current issue | 20/Nov - 20/Nov
Truong | Research how to create decision tree (R or Python?) | Milestone meeting 1. Summarize work done this week and discuss the next step 2. Knowledge sharing 3. Troubleshoot current issue | 20/Nov - 20/Nov
Luu | Study how to create Cube | Milestone meeting 1. Summarize work done this week and discuss the next step 2. Knowledge sharing 3. Troubleshoot current issue | 20/Nov - 20/Nov
Duc | Study Fact + Dimension database, Cube's aspect | Milestone meeting 1. Summarize work done this week and discuss the next step 2. Knowledge sharing 3. Troubleshoot current issue | 20/Nov - 20/Nov
Tuan | Research how to create decision tree (R or Python?) | Milestone meeting 1. Summarize work done this week and discuss the next step 2. Knowledge sharing 3. Troubleshoot current issue | 20/Nov - 20/Nov

## 20-Nov-2015
Team members | Work Done | Next plan | ETA | Risk/Issue
Bach | Milestone meeting 1. Summarize work done this week and discuss the next step 2. Knowledge sharing 3. Troubleshoot current issue | Daily management
Trung | Milestone meeting 1. Summarize work done this week and discuss the next step 2. Knowledge sharing 3. Troubleshoot current issue | Design database following Fact + Dimension standard | 23/Nov - 24/Nov
Truong | Milestone meeting 1. Summarize work done this week and discuss the next step 2. Knowledge sharing 3. Troubleshoot current issue | Create decision tree | 26/Nov - 28/Nov
Luu | Milestone meeting 1. Summarize work done this week and discuss the next step 2. Knowledge sharing 3. Troubleshoot current issue | Create Cube | 25/Nov - 26/Nov
Duc | Milestone meeting 1. Summarize work done this week and discuss the next step 2. Knowledge sharing 3. Troubleshoot current issue | Design database following Fact + Dimension standard | 23/Nov - 24/Nov
Tuan | Milestone meeting 1. Summarize work done this week and discuss the next step 2. Knowledge sharing 3. Troubleshoot current issue | Create decision tree | 26/Nov - 28/Nov

## 23-Nov-2015
Team members | Work Done | Next plan | ETA | Risk/Issue
Bach | Daily management | Daily management
Trung | Design database following Fact + Dimension standard | Design database following Fact + Dimension standard | 23/Nov - 24/Nov
Truong | Technical support on the Fact+Dimension task | Create decision tree | 26/Nov - 28/Nov
Luu | Technical support on the Fact+Dimension task | Create Cube | 25/Nov - 26/Nov
Duc | Design database following Fact + Dimension standard | Design database following Fact + Dimension standard | 23/Nov - 24/Nov
Tuan | Technical support on the Fact+Dimension task | Create decision tree | 26/Nov - 28/Nov

## 24-Nov-2015
Team members | Work Done | Next plan | ETA | Risk/Issue
Bach | Daily management | Daily management
Trung | Design database following Fact + Dimension standard | Classify | 25/Nov - 28/Nov
Truong | Technical support on the Fact+Dimension task | Create decision tree | 26/Nov - 28/Nov
Luu | Technical support on the Fact+Dimension task | Create Cube | 25/Nov - 26/Nov
Duc | Design database following Fact + Dimension standard | Classify | 25/Nov - 28/Nov
Tuan | Technical support on the Fact+Dimension task | Create decision tree | 26/Nov - 28/Nov

## 25-Nov-2015
Team members | Work Done | Next plan | ETA | Risk/Issue
Bach | Daily management | Daily management
Trung | Classify | Classify | 25/Nov - 28/Nov
Truong | Technical support on the Classify task | Create decision tree | 26/Nov - 28/Nov
Luu | Create Cube | Create Cube | 25/Nov - 26/Nov
Duc | Classify | Classify | 25/Nov - 28/Nov
Tuan | Technical support on the Classify task | Create decision tree | 26/Nov - 28/Nov

## 26-Nov-2015
Team members | Work Done | Next plan | ETA | Risk/Issue
Bach | Daily management | 1. Daily management 2. Create final slide for the presentation | 27/Nov - 28/Nov
Trung | Classify | Classify | 25/Nov - 28/Nov
Truong | Create decision tree | Create decision tree | 26/Nov - 28/Nov
Luu | Create Cube | Using Tableau to generate the report | 27/Nov - 28/Nov
Duc | Classify | Classify | 25/Nov - 28/Nov
Tuan | Create decision tree | Create decision tree | 26/Nov - 28/Nov

## 27-Nov-2015
Team members | Work Done | Next plan | ETA | Risk/Issue
Bach | Daily management Create final slide for the presentation | 1. Daily management 2. Create final slide for the presentation 3. Sum-up meeting to summarize the "mini project" | 27/Nov - 28/Nov
Trung | Classify | 1. Classify 2. Sum-up meeting to summarize the "mini project" | 25/Nov - 28/Nov
Truong | Create decision tree | 1. Create decision tree 2. Sum-up meeting to summarize the "mini project" | 26/Nov - 28/Nov
Luu | Using Tableau to generate the report | 1. Using Tableau to generate the report 2. Sum-up meeting to summarize the "mini project" | 27/Nov - 28/Nov
Duc | Classify | 1. Classify 2. Sum-up meeting to summarize the "mini project" | 25/Nov - 28/Nov
Tuan | Create decision tree | 1. Create decision tree 2. Sum-up meeting to summarize the "mini project" | 26/Nov - 28/Nov

## 28-Nov-2015
Team members | Work Done | Next plan | ETA | Risk/Issue
Bach | Daily management Create final slide for the presentation Summarize the whole process | Present output
Trung | Classify Summarize the whole process | Present output
Truong | Create decision tree Summarize the whole process | Present output
Luu | Create Cube Summarize the whole process | Present output
Duc | Classify Summarize the whole process | Present output
Tuan | Create decision tree Summarize the whole process | Present output